## Dashboard
SJTDM TAZ Migration and Data Validation – Project Control Workbook
Project | SJTDM TAZ Migration and Data Validation | Metric | Formula / Source | Current Count | Notes | Action
Lead | Kent Schellinger | Open Tasks | Task_Register Status not Complete | 15 | Formula driven | Review weekly
Current Phase | Data Inventory and System Documentation | Blocked Tasks | Task_Register Status = Blocked | 0 | Formula driven | Resolve blockers
Workbook Purpose | Track files, mirroring, tasks, standards compliance, and QA/QC exceptions | Files Requiring Mirror | File_Mirroring MirrorRequired = Yes | 9 | Formula driven | Confirm target path
Created |  | Files Not Mirrored | Mirror required but status not Mirrored | 9 | Formula driven | Copy to standard location
Repository | SJTDM_TAZ_Migration | Open QA/QC Exceptions | QAQC_Register Status not Complete/N/A | 6 | Formula driven | Review exceptions
Authoritative GIS Products | Mirrored to SJTPO GIS standard locations as required | Standards Items Incomplete | Standards_Compliance Status not Complete/N/A | 7 | Formula driven | Update compliance

## Task_Register
TaskID | Phase | Task | Priority | Owner | Priority2 | DueDate | Status | Dependency | Deliverable | RepoPath | SJTPOStandardPath | Notes
T-001 | Project Foundation | Establish Git repository and folder structure | High | Kent | High |  | Complete |  | README.md | README.md |  | Initial repo created.
T-002 | Project Foundation | Complete project charter | High | Kent | High |  | In Progress | T-001 | Project Charter | docs/charter/project_charter.md
T-003 | Standards | Develop file mirroring inventory | High | Kent | High |  | In Progress | T-001 | File mirroring tracker | docs/standards/file_mirroring_inventory.xlsx |  | This workbook is first draft.
T-004 | Standards | Review SJTPO GIS Data Management requirements | High | Kent | High |  | Not Started |  | Database inventory | data/raw/Access
T-005 | Model Discovery | Inventory Cube scripts | Inventory all Cube Voyager scripts and identify execution order. | Kent | High |  | Not Started | T-001 | Cube Script Inventory | data/intermediate/Inventories |  | Foundation for model documentation.
T-006 | Model Discovery | Inventory Cube input files | Identify all model inputs referenced by Cube scripts. | Kent | High |  | Not Started | T-005 | Input File Inventory | data/intermediate/Inventories |  | Includes DBFs, CSVs, networks and lookup tables.
T-007 | Model Discovery | Catalog SJTDM tables and fields | Validate existing table inventory and classify table purpose. | Kent | High |  | In Progress | T-005 | Table Catalog | data/intermediate/Inventories |  | Excel inventory already exists.
T-008 | Model Discovery | Identify TAZ-dependent tables | Determine which tables contain zonal data affecting model results. | Kent | High |  | In Progress | T-007 | TAZ Dependency Matrix | docs/methodology |  | Critical migration task.
T-009 | Data Lineage | Trace socioeconomic data sources | Document source-to-model workflow for population and households. | Kent | High |  | Not Started | T-008 | Data Lineage Documentation | docs/methodology |  | Supports QA/QC.
T-010 | Data Lineage | Trace employment data sources | Document source-to-model workflow for employment variables. | Kent | High |  | Not Started | T-008 | Employment Lineage Documentation | docs/methodology |  | Supports trip attraction validation.
T-011 | Data Lineage | Trace recreational trip data sources | Document source-to-model workflow for recreational trip generation. | Kent | High |  | Not Started | T-008 | Recreation Lineage Documentation | docs/methodology |  | Supports recreational TAZ migration.
T-012 | TAZ Migration | Develop migration methodology | Document methodology for transition from legacy TAZs to 2020 TAZs. | Kent | High |  | In Progress | T-011 | Migration Methodology | docs/methodology |  | Core project objective. First-pass review of recreational model TAZs completed. TAZs containing significant recreational land-use patterns and sub-census-block characteristics identified. Findings indicate that preservation of model-relevant land-use geography is more important than geometric similarity between legacy and proposed TAZ boundaries.
T-013 | TAZ Migration | Develop crosswalk methodology | Document allocation and split/merge procedures. | Kent | High |  | Not Started | T-012 | Crosswalk Methodology | docs/methodology |  | Recreational model screening methodology tested. Initial review confirms geometry-only comparisons are insufficient for evaluating migration quality. QA/QC framework shall evaluate preservation of socioeconomic and recreational model characteristics in addition to geometric correspondence.
T-014 | Validation | Define preservation metrics | Establish validation metrics for households, population and employment. | Kent | High |  | Not Started | T-013 | Validation Framework | docs/qa_reports |  | Replaces geometry-only QA/QC.
T-015 | Validation | Build validation procedures | Develop queries and reports to evaluate preservation metrics. | Kent | High |  | Not Started | T-014 | Validation Procedures | docs/qa_reports |  | Automated where possible.

## File_Mirroring
FileName | FileType | ProjectRepoPath | SJTPOStandardPath | AuthoritativeLocation | MirrorRequired | LastMirroredDate | Status | RelatedTaskID | Notes
README.md | Markdown | README.md |  | Git Repository | No |  | N/A | T-001 | Project overview only.
project_charter.md | Markdown | docs/charter/project_charter.md |  | Git Repository | No |  | Not Started | T-002 | Create next.
file_mirroring_inventory.xlsx | Excel | docs/standards/file_mirroring_inventory.xlsx | TBD | Git Repository | Yes |  | In Progress | T-003 | This workbook; mirror path to be confirmed.
SJTPO GIS Data Management Standards Memorandum | PDF | docs/source_documents/GIS_Standards | TBD | SJTPO GIS Standard Location | Yes |  | TBD | T-006 | Copy authoritative document to expected standard location and reference copy in repo.
SJTDM_INPUTS.accdb | Access | data/raw/Access | TBD | SJTPO GIS Standard Location | Yes |  | TBD | T-004 | Likely too large/binary for meaningful Git versioning; track location and version.
Cube table inventory workbook | Excel | data/intermediate/Inventories | TBD | Git Repository | Yes |  | TBD | T-007 | Placeholder for existing discovered table inventory.
TAZ comparison workbook | Excel | data/intermediate/QAQC | TBD | Git Repository | Yes |  | TBD | T-010 | Placeholder for existing QA/QC workbook.
SJTDM_TAZ_Migration_Project_Control.xlsx | Excel | docs/standards |  | Git Repository | Yes |  | In Progress | T-003 | Master project tracker.
SJTDM_Master_Tables_With_Fields.xlsx | Excel | data/intermediate/Inventories |  | Git Repository | Yes |  | Not Started | T-007 | Table inventory workbook.
SJTDM_INPUTS_Data.accdb | Access | data/raw/Access |  | SJTPO Standard Location | Yes |  | Not Started | T-007 | Source database.
SJTDM Users Guide.pdf | PDF | docs/source_documents |  | SJTPO Standard Location | Yes |  | Not Started | T-009 | Primary documentation.

## Data_Inventory
InventoryID | DatasetOrTable | SourceType | SourceSystem | ProjectRepoPath | SJTPOStandardPath | PrimaryKey | TemporalVintage | GeographicLevel | ModelUse | Status | Owner | Notes
DI-001 | Legacy SJTDM TAZ socioeconomic inputs | Access/Table | SJTDM_INPUTS.accdb | data/raw/Access | TBD | TAZ | Legacy model | TAZ | Trip generation / attraction | Not Started | Kent
DI-002 | Cube Voyager input tables | Cube/Database | SJTDM Cube model | data/intermediate/Inventories | TBD | Varies | Legacy model | TAZ / Network | Model execution | Not Started | Kent
DI-003 | 2010 Census Blocks | GIS/Census | US Census | data/raw/Census | TBD | GEOID10 | 2010 | Block | Legacy geographic relationship | Not Started | Kent
DI-004 | 2020 Census Blocks | GIS/Census | US Census | data/raw/Census | TBD | GEOID20 | 2020 | Block | New TAZ construction | Not Started | Kent
DI-005 | SJTDM_Master_Tables_With_Fields.xlsx | Excel | SJTDM Inventory | data/intermediate/Inventories |  | TableName | 2026 | Model System | Documentation | Complete | Kent | Contains inventoried SJTDM tables and fields.
DI-006 | SJTDM_INPUTS_Data.accdb | Access Database | SJTDM | data/raw/Access |  | Varies | Legacy | Multiple | Model Inputs | In Progress | Kent | Primary source database for discovery.
DI-007 | Cube Voyager Scripts | Script Collection | SJTDM | data/raw/Cube |  | ScriptName | Legacy | Model System | Model Execution | Not Started | Kent | Inventory pending.
DI-008 | SJTDM Users Guide | PDF | SJTDM Documentation | docs/source_documents |  | N/A | 2010 | N/A | Documentation | Not Started | Kent | Primary model documentation.

## Standards_Compliance
StandardID | StandardArea | Requirement | ProjectImplementation | EvidencePath | Status | Owner | Notes | Column1 | Column2 | Column3 | Column4 | Column5
SC-001 | Directory Structure | Use standard project directory structure for GIS data and deliverables. | Repo structure created; SJTPO standard mirror paths to be confirmed. | README.md; File_Mirroring | In Progress | Kent
SC-002 | Metadata | Maintain metadata records for final GIS datasets and authoritative products. | Metadata folder created; records not yet populated. | metadata | Not Started | Kent
Q-003 | Model Discovery | SJTDM Tables | Table Usage | Documentation Review | Identify active model inputs | Distinguish active tables from legacy artifacts. | In Progress | High | Kent | Pending Cube script review. | data/intermediate/Inventories | Key discovery task.
Q-004 | Data Lineage | Socioeconomic Inputs | Population and Households | Source Trace | Complete lineage required | Source workflow not fully documented. | Not Started | High | Kent | TBD | docs/methodology | Required before validation.
Q-005 | TAZ Migration | TAZ-dependent tables | Multiple | Inventory | All TAZ tables identified | Unknown number of TAZ-sensitive tables. | Not Started | High | Kent | TBD | Table Inventory | Critical project risk.
Q-006 | Validation | TAZ Migration Variables | Multiple | Validation Framework | Preservation metrics established | Validation methodology not yet defined. | Not Started | High | Kent | TBD | docs/qa_reports | Required before migration QA/QC.

## QAQC_Register
IssueID | Category | DatasetOrTable | FieldOrVariable | CheckType | ThresholdOrRule | IssueDescription | Status | Priority | Owner | Resolution | EvidencePath | Notes
Q-001 | Methodology | TAZ comparison | Geometry | Scope control | Geometry is supporting diagnostic only | Prior geometry-only QA/QC does not represent model behavior. | In Progress | High | Kent | Reframe process around model data content. | docs/methodology
Q-002 | Crosswalk | 2011 TAZ to 2020 geography | TAZ relationship | Manual review | Flag many-to-many relationships | Legacy TAZs may not align cleanly to 2010 or 2020 blocks. | Not Started | High | Kent |  | data/intermediate/Crosswalks
Q-003 | Data Inventory | Cube tables | Field usage | Traceability | Each model-used field must be identified | Need to distinguish active Cube inputs from legacy artifacts. | Not Started | High | Kent |  | data/intermediate/Inventories
Q-004 | Validation | Population / households | TAZ totals | Tolerance TBD | Regional/county/municipal aggregation checks required | TAZ-to-TAZ comparison alone will be noisy. | Not Started | Medium | Kent |  | data/intermediate/QAQC
Q-005 | Validation | Employment | Employment fields | Tolerance TBD | Employment preservation must be checked by type if fields exist | Need source system and field definitions. | Not Started | High | Kent |  | data/intermediate/QAQC

## Lookup_Lists
Status | Priority | YesNo | AuthoritativeLocation
Not Started | High | Yes | Git Repository
In Progress | Medium | No | SJTPO GIS Standard Location
Blocked | Low | TBD | Access Database
Under Review | Critical |  | External Source
Complete
Deferred
N/A